## Sheet1
S NO | Features | Sub Category | Description | Staus | Remarks
1 | Dashboard | Master/Super Admin | Compliance Overview: Real-time insights into compliance posture, key compliance activities, risks, and policies. Notifications: Alerts and reminders for important actions and updates. Organizational Summary: List of all onboarded organizations. Count of onboarded channel partners. Number of frameworks sold and total frameworks in use. Financial Insights: Billing information with details on upcoming payments, overdue bills, and framework renewals (organization-wise). Revenue breakdown per channel partner. Top Clients: Highlights of the top 5 clients based on activity or revenue. Storage Information: Detailed storage usage by organization, showing allocated, used, and free storage. Revenue and Performance Charts: Visuals showing revenue trends, payment schedules, and upcoming framework renewals. This dashboard combines critical compliance, financial, and client insights to support effective decision-making and streamlined management. | Not yet started | Multi tenancy to be discussed, SaaS model, packages, etc.
| Dashboard | Partner Dashboard | Client Portfolio: Displays the number of organizations each partner has resold to as a channel partner. Billing Insights: Amount to be collected from each client. Comprehensive billing information for easier financial tracking. Special Offers: Available offers for partners to enhance service value. Notifications: Key updates and reminders for important tasks and deadlines. This partner dashboard enables clear oversight and streamlined management of compliance tasks, client portfolios, and billing. | Not yet Started | Multi tenancy to be discussed, SaaS model, packages, etc.
| Dashboard | Admin | Compliance Overview: Quick view of key compliance activities and policies. Risk Management: At-a-glance insights into current risks and potential threats. Policy Updates: Access to essential policy information in real-time. Real-Time Insights: Up-to-date data on compliance posture, enabling immediate decision-making. Task Monitoring: Overview of assigned and pending tasks to ensure timely completion. Alert Notifications: Immediate alerts for prompt action and efficient tracking. | Ongoing | 2024-10-29
| Dashboard | Implementor | Compliance Activities: Displays essential compliance tasks and updates. Risk Management: Provides a summary of current risks and potential issues. Policy Information: Quick access to critical policies for reference. Real-Time Insights: Keeps organizational compliance posture updated. Task Tracking: Monitors task completion and alerts as necessary. Decision Support: Facilitates fast decision-making and action tracking. | Ongoing | 2024-10-29
| Dashboard | Assignee | Customizable Task Management: Tailors dashboard to each assignee’s individual responsibilities. Policy Visibility: Provides relevant policies aligned with their assigned tasks. Real-Time Updates: Ensures tasks are always up-to-date for timely completion. Accessibility: Centralizes access to assigned tasks and compliance requirements. | Ongoing | 2024-11-05
| Dashboard | Approver | Approval Focused: Displays pending approvals across policies and tasks. Compliance Assurance: Supports review and confirmation of compliance standards. Workflow Optimization: Simplifies review process for faster approvals. | Ongoing | 2024-11-05
| Dashboard | Internal Auditor | Compliance Review Tools: Equipped with tools to monitor and evaluate internal compliance practices. Risk Assessment: Offers mechanisms to assess and document risk factors. Policy Adherence Tracking: Tracks adherence to internal policies to identify gaps. Regular Compliance Reviews: Facilitates routine reviews to highlight areas for improvement and maintain standards. | Ongoing | 2024-11-12
| Dashboard | External Auditor | High-Level Compliance Overview: Provides a summary of the organization’s overall compliance status. Audit Records Access: Organizes audit records and documents for easy retrieval. Framework Documentation: Centralizes framework-specific documentation for transparent review. Clear Information Access: Streamlines access to compliance data, allowing auditors to validate compliance quickly and efficiently. | Ongoing | 2024-11-13
2 | Framework | Controls | All Controls are uploaded and mapped, however, validation is going one | Completed | 2024-11-05
| Framework | ISO 27001:2022 | Supports major compliance frameworks like GDPR, ISO 27001:2022, SOC 2, RBI Cybersecurity Framework (CSF), and PCI DSS, allowing businesses to adhere to industry regulations. It helps in aligning policies and processes with these frameworks and tracking progress toward certification. | Completed
| Framework | GDPR |  | Completed | Framework Functionality is done. Verified Controls will be uploaded by 5th Nov
| Framework | PCI-DSS V3 |  | Completed | Framework Functionality is done. Verified Controls will be uploaded by 5th Nov
| Framework | PCI-DSS V4 |  | Completed | Framework Functionality is done. Verified Controls will be uploaded by 5th Nov
| Framework | SOC 2 Type2 |  | Completed | Framework Functionality is done. Verified Controls will be uploaded by 5th Nov
| Framework | RBI-CSF |  | Completed | Framework Functionality is done. Verified Controls will be uploaded by 5th Nov
| Framework | RBI-SAR |  | Completed | Framework Functionality is done. Verified Controls will be uploaded by 5th Nov
| Framework | NIST 800 |  | Completed | Framework Functionality is done. Verified Controls will be uploaded by 5th Nov
| Framework | HIPPA |  | Completed | Framework Functionality is done. Verified Controls will be uploaded by 5th Nov
| Framework | ISO 9001 |  | Not yet Started | Compliance Head will start this by next week and get tth
| Framework | ISO 20000 |  | Not yet Started | Compliance Head will start this by next week and get tth
| Framework | ISO 31000 |  | Not yet Started | Compliance Head will start this by next week and get tth
| Framework | IRDA |  | Not yet Started | Compliance Head will start this by next week and get tth
| Framework | ALL BANKING |  | Not yet Started | Compliance Head will start this by next week and get tth
| Framework | ALL Insurance Frameworks across the globe |  | Not yet Started | Compliance Head will start this by next week and get tth
3 | Policy |  | Allows for the creation, management, and distribution of company policies. It ensures that all employees have access to updated policies and supports compliance by ensuring policies are reviewed, approved, and acknowledged regularly. | Completed | Functionality is done, testing is pending. In policy builder, draft policy is getting uploades and created
4 | Evidence Task |  | Manages evidence collection tasks for compliance audits. Assigns tasks to employees to gather required documentation, track progress, and ensure timely submission, streamlining audit readiness. | Completed | Functionality is done, testing is pending. Suggested several changes like providing inbuilt tracker format to update the details live.
5 | People | Employee Security Awareness | Tracks employees and their roles within compliance, including Security Awareness training. Ensures that all personnel are compliant with the necessary training and certifications, contributing to overall organizational security. | Completed | Edit option to be made/added
6 | Purplecop Trust | Document NDA | Handles sensitive documents like Non-Disclosure Agreements (NDAs) and other trust-related documentation, ensuring they are securely stored, easily accessible, and version-controlled to maintain compliance with regulations. | Ongoing | Will be completed by 29th Oct'24
7 | Asset Register |  | Maintains a comprehensive register of all assets, including hardware, software, and data, ensuring that assets are monitored and managed in line with compliance frameworks. This supports better tracking and management of organizational resources. | Completed | Completed
8 | Risk Register |  | Allows for the documentation and tracking of risks associated with the business. Includes the identification, analysis, and prioritization of risks to ensure effective mitigation strategies are in place. | Completed
9 | Corrective Action |  | Enables the identification, documentation, and tracking of corrective actions for any issues that arise from audits or risk assessments. Ensures timely resolution to mitigate potential compliance violations. | Completed
10 | Audit Center |  | Centralizes all internal and external audits, allowing teams to prepare, track, and manage audits efficiently. Provides a platform for managing audit requirements, findings, and remediation actions. | Completed
11 | Reporting | Monitoring Compliance | Offers comprehensive reporting tools for Monitoring and tracking Compliance with relevant standards. This feature provides visual data representations, export options, and customizable reports to support compliance management and decision-making. | Completed
12 | Client | Organization | Manages Organization details for client businesses, keeping track of compliance-related data and documentation relevant to each client. Ensures a centralized view of client relationships, roles, and responsibilities in compliance activities. | Completed
13 | Settings | Asset Risk | Provides customizable settings for managing key configurations related to Asset management and Risk assessment, allowing for tailored compliance solutions suited to the organization’s specific needs. | Completed
14 | Integration | APIs | Will ensure to fetch the relevant details across the tools to automate the process and keep upto date compliant | Not yet Started | Start Date to be discussed
15 | TPRM | Independant module |  | Not yet Started | To be started on 11th November
16 | CSPM | Independant module |  | Not yet Started | Start Date to be discussed
17 | VM | Independant module |  | Not yet Started | Start Date to be discussed

## Sheet2
Sr No | Name | Link | ID | Pswd
1 | Admin | http://beta.instagrc.com/login | isfar@technivorus.com | Urooj@1023
2 | Implementar | http://beta.instagrc.com/login | implementor@grc.com | cubispace@123
3 | Assignee | http://beta.instagrc.com/login | assignee@grc.com | cubispace@123
4 | Approver | http://beta.instagrc.com/login | approver@grc.com | cubispace@123
5 | Internal Auditor | http://beta.instagrc.com/login | i.auditor@grc.com | cubispace@123
6 | External Auditor